TERMS OF REFERENCE (ToR)

Independent Consultant to Lead, Facilitate, and Conduct the Mid-Term Review (MTR)

Project Title: Scaling and Operationalization of Pluralistic Last-Mile Delivery, Extension and Advisory Services in Africa

Contract No. AFAAS/AGRA/CQS/2026/0001

Funder: Alliance for a Green Revolution in Africa (AGRA)

Implementation Period: August 2024 – March 2027

Review Period: August 2024 – December 2025

1. BACKGROUND

Africa’s agricultural systems are undergoing structural transitions; however, many smallholder farmers remain excluded from quality, timely, and relevant extension services. Public sector-led systems have limited reach and responsiveness, while private sector-led and digital advisory innovations remain fragmented and under-leveraged.

In response, the African Forum for Agricultural Advisory Services (AFAAS), in partnership with the Alliance for a Green Revolution in Africa (AGRA), is implementing a regional initiative titled “Scaling and Operationalization of Pluralistic Last-Mile Delivery, Extension and Advisory Services in Africa.” The project is being implemented in five AGRA-supported countries—Burkina Faso, Malawi, Nigeria, Rwanda, and Uganda—and seeks to modernize and decentralize Agricultural Extension and Advisory Services (AEAS) in order to increase productivity, market access, and resilience among smallholder farmers, particularly women and youth.

The project is grounded on three interlinked pillars:

- The digitalization of inclusive, farming system-specific extension content;

- The development and operationalization of last-mile AEAS business models, including youth and women agro-entrepreneurs; and

- The institutionalization of enabling policy, coordination, and knowledge platforms to support pluralistic AEAS systems.

AFAAS is leveraging its network of national-level Country Fora as the implementing arms of the project. Through Direct Commissioned Sub-Grants, each Country Forum is responsible for localizing interventions, leading implementation, fostering partnerships with private sector actors and government institutions, and ensuring that marginalized farming populations are empowered with actionable knowledge and services.

With the project now beyond the midpoint of its life-cycle, it is critical to undertake a structured Mid-Term Review (MTR) to systematically assess progress against planned objectives, identify operational and institutional bottlenecks, document emerging outcomes and innovations, and provide evidence-based recommendations to enhance delivery in the final third of the project.

Given that AFAAS and the Country Fora are responsible for project implementation, conducting the review internally would present a conflict of interest. Consequently, AFAAS will engage an independent consultant to lead and conduct the Mid-Term Review in order to ensure objectivity, impartiality, and credibility, while strengthening accountability, learning, and sustainability planning.

2. PURPOSE OF THE CONSULTANCY

The purpose of this consultancy is to lead, facilitate, and conduct the Mid-Term Review (MTR) of the AGRA-funded project, based strictly on the approved objectives, scope, methodology, and evaluation framework. The Mid-Term Review will assess progress on project implementation, determine whether the project is on track to meet its defined goals and objectives, document innovations and good practices, identify constraints and bottlenecks to implementation, and generate evidence and insights to inform adjustments and refinements to implementation strategies, methodologies, and partnerships, without violating AGRA grant conditions.

3. OBJECTIVES OF THE CONSULTANCY

3.1 Overall Objective

To undertake a comprehensive review of technical, financial, institutional, and compliance performance of the AGRA-funded project implemented by AFAAS and its five Country Fora, with the aim of strengthening results delivery, learning, and sustainability.

3.2 Specific Objectives

The consultant will support AFAAS to:

- Assess technical progress against project outputs, indicators, and milestones, and how these contribute to the project objectives and goal.

- Evaluate efficiency in project delivery, and assess organizational compliance with AGRA’s and AFAAS fiduciary conditions.

- Assess the effectiveness of the delivery mechanisms of the project.

- Identify challenges and implementation bottlenecks, including risks at institutional, operational, and systemic levels.

- Generate forward-looking recommendations to enhance performance, partnerships, and sustainability in the final implementation phase.

4. SCOPE OF THE MID-TERM REVIEW

4.1 Geographic Scope

The Mid-Term Review will cover the AFAAS Secretariat and all five implementing countries: Burkina Faso, Malawi, Nigeria, Rwanda, and Uganda.

4.2 Thematic and Compliance Scope

The review will focus on how project results are contributing to the project objectives and goal, and will include assessment of compliance with AJGRA requirements, grants management policies, safeguards framework, Monitoring, Evaluation and Learning (MEL) guidelines, and conflict-of-interest protocols.

5. REVIEW METHODOLOGY

The Mid-Term Review will adopt a structured and multi-phased methodology to enable a rigorous, participatory, and forward-looking review of the project.

The review will focus on five thematic pillars:

- Performance

- Financial accountability

- Institutional capacity

- Testing project assumptions

- Risk analysis

Phase I: Desk Review and Virtual Consultations

The consultant will conduct a comprehensive desk-based analysis complemented by virtual consultations. This phase will examine project documents, project reports, and results frameworks in order to establish causal relationships between project outputs and objectives and identify emerging patterns.

Activity–Output–Outcome–Impact Contribution Analysis

The consultant will assess progress across all outputs by:

- Reviewing implementation milestones and outputs against targets in the Results Framework;

- Analyzing the quality and relevance of project results to the project objectives;

- Verifying access to outputs by targeted beneficiaries, including women, youth, and marginalized groups;

- Assessing the contribution of outputs to outcomes and to the overall impact of the project;

- Reviewing gender and youth mainstreaming in delivery models and beneficiary targeting;

- Examining climate-smart practices supported and their integration in AEAS content.

Financial Management, Internal Controls, and Procurement Assessment

The consultant will undertake a deep-dive review of the financial and fiduciary aspects of the project, which will also serve as a capacity-building process for implementing partners. This will include:

- Analysis of fund disbursement flows and budget execution across implementing partners;

- Assessment of alignment between financial burn rates and technical delivery progress;

- Assessment of cost-effectiveness and value-for-money issues;

- Review of adherence to AFAAS and AGRA fiduciary standards, including audit readiness considerations.

Phase II: Validation and Planning Workshop

The consultant will organize and facilitate a consultative validation and planning workshop involving AFAAS Secretariat, implementing partners, AGRA, and other key stakeholders. The workshop will aim to:

- Present and discuss findings from the desk review;

- Validate performance ratings and narrative insights;

- Engage in joint reflection on implementation bottlenecks and adaptive measures, including identification of institutional gaps and support needs;

- Plan for post-project sustainability, including scaling strategies and policy integration;

- Develop a costed and time-bound plan for the remaining 12 months of implementation;

- Update the project risk matrix and mitigation measures.

6. EVALUATION DESIGN

The Mid-Term Review will be based on evaluation criteria established by the Organisation for Economic Co-operation and Development (OECD) and the Development Assistance Committee (DAC), including:

- Relevance

- Effectiveness

- Impact

- Sustainability

The consultant will apply contribution and content analysis methodologies. The evaluation questions will be descriptive and normative in nature and will be detailed in an evaluation matrix developed by the consultant.

7. EXPECTED DELIVERABLES

The consultant will deliver the following:

- Inception Report, including detailed methodology, evaluation matrix, tools, and workplan;

- Draft Mid-Term Review Report with detailed findings, compliance assessment, lessons learned, good practices, and recommendations;

- Facilitation and documentation of the validation and planning workshop;

- Updated Risk and Mitigation Matrix reflecting project vulnerabilities and proposed safeguards;

- Final Mid-Term Review Report incorporating feedback from AFAAS, Country Fora, and AGRA.

8. DURATION AND TIMELINE

The consultancy will be implemented in line with the following indicative timeline:

- Design and sharing of tools: 1–5 December 2025

- Desk review and self-assessments: 5–18 December 2025

- Draft report preparation: 5–14 January 2026

- Validation workshop: 18–23 January 2026

- Final report submission: 31 January 2026

9. MANAGEMENT AND COORDINATION ARRANGEMENTS

- The consultant will work under the coordination of the AFAAS Monitoring, Evaluation and Learning (MEL) Unit, which will oversee review design, tools development, reporting, and engagement with AGRA.

- Country Forum MEL Officers will facilitate data collection, virtual consultations, and stakeholder engagement at country level.

- The AGRA MEL Team will provide oversight, technical input, and participate in validation processes.

- The AFAAS Finance Team will support the review of fiduciary, financial, and compliance aspects.

10. CONSULTANT QUALIFICATIONS AND EXPERIENCE

The consultant should demonstrate:

- The consultant should possess at least a Masters’ degree in Development Economics, Agricultural and Applied Economics, Statistics, Agricultural Extension, Development studies and any other relevant field

- Post graduate Diploma in Monitoring and Evaluation, or project Planning and Management will be an added advantage

- At least five (5) years of demonstrated experience in conducting project evaluations of multi-country development project and donor driven development projects;

- Demonstrated understanding and experience in apply the OECD/DAC evaluation criteria in project

- Strong facilitation, analytical, and report-writing skills;

11. ETHICS, INDEPENDENCE, AND CONFIDENTIALITY

The consultant must be independent of the project implementation and declare any potential conflict of interest. All information accessed during the assignment must be treated as confidential, and the consultant must adhere to applicable conflict-of-interest protocols.